## Rock Canvas
ROCK CANVAS
90-Day Transformation Sprint
ROCK DEFINITION
Rock Name: | [Your 90-day transformational goal]
Owner: | [Single person accountable - must spend 25%+ time on this]
Start Date: | [Week 1, Day 1]
Target Completion: | [90 days from start]
THE PROBLEM
What is the bottleneck?
[Describe the specific bottleneck slowing everything down]
THE PHYSICS ⭐ CRITICAL
What are the actual mechanics creating this delay?
Describe: sequential dependencies, approval chains, handoffs, waiting periods that create the bottleneck. Example: 'Sequential approvals through 14 systems create 41 days of waiting for 90 minutes of actual work'
THE OUTCOME
Current state: | [Current baseline metric]
Target state: | [Specific, measurable target]
Measurement: | [How success is measured]
Success Criteria (Done looks like):
1. | [Specific success criterion]
2. | [Specific success criterion]
3. | [Specific success criterion]
4. | [Specific success criterion]
MILESTONES (Every 2 weeks)
Week | Milestone
1-2 | [What will be accomplished]
3-4 | [What will be accomplished]
5-6 | [What will be accomplished]
7-8 | [What will be accomplished]
9-10 | [What will be accomplished]
11-12 | [What will be accomplished]
13 (COMPLETE) | [What will be accomplished]
ROCK OWNER CHECKLIST
☐ Deep frustration with the current state
☐ Detailed knowledge of the actual process
☐ Respect from operational teams
☐ Willingness to break rules (except regulations)
☐ No political agenda or empire to protect
☐ Track record of building workarounds
☐ Available 50%+ time for 90 days
RESOURCES NEEDED
Budget: | $ [Discretionary budget for Rock Owner]
People: | [Number of team members and % time commitment]
Technology: | [Tools/software needed]
External Support: | [Consultants/contractors if needed]
OBSTACLES & MITIGATION
Obstacle 1: | [What could block success?]
Mitigation 1: | [How will you address this?]
Obstacle 2: | [What could block success?]
Mitigation 2: | [How will you address this?]
Obstacle 3: | [What could block success?]
Mitigation 3: | [How will you address this?]
AUTHORITY PACKAGE
☐ Change any process that doesn't violate regulations
☐ Eliminate any approval that isn't legally required
☐ Redesign workflows without committee approval
☐ Select team members from any department
☐ Direct line to CEO, bypassing hierarchy
☐ Weekly CEO check-in (15 minutes max)
☐ Public executive support announcement
☐ Immunity from political retaliation
🚩 RED FLAGS
• Rock Owner changed mid-sprint = Almost always failure
• Success criteria changed = Managing perception, not solving problems
• No measurable progress for 2+ weeks = Blocked, needs CEO intervention
• Rock Owner spending <25% time = Not a real Rock
• Team keeps changing = Prevents momentum
• Scope creep = Dilutes focus